## List of Service
Stick-Built | Module | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours (internal) | Estimated hours (external) | Start date | Due date | Notes | Professional Role
Yes | No |  | Fabrication Setup | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 180 | 200 |  |  |  | XXXXXX_Fabrication Manager
No | Yes |  | Fabrication Execution Strategy | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 180 | 200 |  |  |  | XXXXXX_Fabrication Manager
Yes | No |  | Shop Drawing Steel Structure - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Shop Drawing Piping - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 9 | 10 |  |  |  | 432186_Construction Engineer
Yes | No |  | Shop Drawing Piping Support - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Shop Drawing Steel Structure - Review | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | - | 840 |  |  | consider 140 hours/monthly (80%) | 432186_Construction Engineer
Yes | Yes |  | DPR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | ADR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Spooling Check List | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen Setting - Setting and Maintenance | Software | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 108 | 120 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen -Training | Training | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 63 | 70 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Analysis of Piping Revisions | Procedure | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 27 | 40 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | DDC (Data Driven Construction) Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 945 | 2500 |  |  | after 60% 3D Model Review (not before) | 432181_Integrated System Specialist
Yes | Yes |  | Virtual Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - | 400 |  |  | optional | 432181_Integrated System Specialist
Yes | Yes |  | Augmented Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | Hold | Hold |  |  | optional | 432181_Integrated System Specialist
Yes | Yes |  | GEMAPI SA - Setting and Maintenance | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 54 | 60 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | GEMAPI SA - Training | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 63 | 70 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | MAGA (Material Management) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes | Yes |  | MAGA (Material Management) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 120 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Completion Dossier - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Completion Dossier - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Punch List - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Hydro Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Pneumatic Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Flange Management Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Mechanical Completion Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 36 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
No | Yes |  | Carry Over Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 63 | 65 |  |  |  | 430006_System Completion Coordinator
Yes | No |  | Feasibility Study - Steel Structure (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | - | 1092 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | No |  | Feasibility Study - Piping (Prefabrication and Erection) | Procedure | FABSI | System Completion | Bardoscia Roberto | Not started | - | 2457 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | No |  | Feasibility Study - Piping support (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | - | 1638 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | Yes |  | Supervision of Steel Structure Stick-Built (Vendor), only UAE Area | Supervision | FABSI | Production Engineering | Sandri Juri | Not started | - | 720 |  |  | consider 72 hours/monthly (40%) | 432186_Construction Engineer
- | - |  | Process Control for Piping Activities Procedure | - | - | - | - | -
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated for one year. Reply: 225 setting 720 manutenzione

## Summary PMP HO
Professional Role | Manhours
XXXXXX_Fabrication Manager | 400
432186_Construction Engineer | 7177
432181_Integrated System Specialist | 4040
430006_System Completion Coordinator | 475

## Software & Hardware
STS |  | WHM |  | VR
Spools estimation: 3 each isometric |  | Mobile Devices: 5/6 each subcontractor/fabrication yard |  | Suggested licences: 3 (2 for the backoffice)
Mobile Devices: 5/6 each subcontractor/fabrication yard
Printers/Tag Stations: 1 each subcontractor/fabrication yard
HW RFID SOLUTION | UNIT COST € | HW BARCODE SOLUTION | UNIT COST € | SW License and Subscription | Annual Cost per User
WHITE TAGS FOR SPOOL TRACKING SYSTEM (RE-USABLE) | 2.2 | ATHESI RUGGED SMARTPHONE | 1050 | Autodesk Workshop XR | 2.000,00 €
TAG STATION - CAEN RFID TILE R1250I | 650 | LABELS WITH PRE-PRINTED BARCODE | 0.55 | Meta Quest for Business | 300,00 €
ATHESI RUGGED SMARTPHONE | 1050
CAEN R1170I QID MINI | 850 | updated data, as of January 2025. |  | Hardware | UNIT COST €
PLASTIC LABEL 3M 80X40MM YELLOW ROLL (1000 EACH) | 125 |  |  | Meta Quest 3 | 750,00 €
HR2 RESIN RIBBON ROLL (2500 EACH) | 18
PRINTER HONEYWELL PD45S | 950 |  |  | updated data, as of January 2025.
HW BARCODE SOLUTION | UNIT COST €
TAG STATION - CAEN RFID TILE R1250I | 650
ATHESI RUGGED SMARTPHONE | 1050
LABELS WITH PRE-PRINTED BARCODE | 0.55
updated data, as of January 2025.

## TemplateList
Stick-Built | Module | Activities | Title | Technical Unit | Assigned to | Progress | Professional Role | Project
Yes | No | Fabrication Setup | Document | Production Engineering | Cannella Antonio | Not started | XXXXXX_Fabrication Manager | General
No | Yes | Fabrication Execution Strategy | Software | Fabrication Engineering | Contreras Cesar Raul | On Progress | 432186_Construction Engineer | Anadarko
- | - | Shop Drawing Steel Structure - Estimation | Training | Pre-Fabrication System | Gioso Alex | Finished | 432181_Integrated System Specialist | Kutei
|  | Shop Drawing Piping - Estimation | Procedure | System Completion | Bardoscia Roberto |  | 430006_System Completion Coordinator | Shah Gas
|  | Shop Drawing Piping Support - Estimation | Supervision | - | Spano Michele |  |  | Venezia
|  | Shop Drawing Steel Structure - Review | - |  | Sandri Juri
|  | DPR Piping - Setting and Maintenance |  |  | -
ADR Piping - Setting and Maintenance
Spooling Check List
Spoolgen Setting - Setting and Maintenance
Spoolgen -Training
Analysis of Piping Revisions
DDC (Data Driven Construction) Setting and Maintenance
Virtual Reality - Setting and Maintenance
Augmented Reality - Setting and Maintenance
GEMAPI SA - Setting and Maintenance
GEMAPI SA - Training
MAGA (Material Management) - Setting and Maintenance
MAGA (Material Management) - Training
Preservation - Setting and Maintenance
Preservation - Training
CARP - Setting and Maintenance
CARP - Training
WiTS (Welding Integrated Tracking System) - Setting and Maintenance
WiTS (Welding Integrated Tracking System) - Training
STS (Spool Tracking System) - Setting and Maintenance
STS (Spool Tracking System) - Training
Support Management - Setting and Maintenance
Support Management - Training
Digital Test Pack - Setting and Maintenance
Digital Test Pack - Training
Completion Dossier - Setting and Maintenance
Completion Dossier - Training
Punch List - Setting and Maintenance
Punch List - Training
Hydro Test Procedure
Pneumatic Test Procedure
Flange Management Procedure
Mechanical Completion Procedure
Punch List Procedure
Carry Over Procedure
Feasibility Study - Steel Structure (Prefabrication and Erection)
Feasibility Study - Piping (Prefabrication and Erection)
Feasibility Study - Piping support (Prefabrication and Erection)
Supervision of Steel Structure Stick-Built (Vendor), only UAE Area
Process Control for Piping Activities Procedure

## Anadarko
Stick-Built | Module | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours (internal) | Estimated hours (external) | Start date | Due date | Notes | Professional Role
Yes | No |  | Fabrication Setup | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 180 | 200 |  |  |  | XXXXXX_Fabrication Manager
No | Yes |  | Fabrication Execution Strategy | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 180 | 200 |  |  |  | XXXXXX_Fabrication Manager
Yes | No |  | Shop Drawing Steel Structure - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Shop Drawing Piping - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 9 | 10 |  |  |  | 432186_Construction Engineer
Yes | No |  | Shop Drawing Piping Support - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Shop Drawing Steel Structure - Review | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | - | 840 |  |  | consider 140 hours/monthly (80%) | 432186_Construction Engineer
Yes | Yes |  | DPR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | ADR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Spooling Check List | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 18 | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen Setting - Setting and Maintenance | Software | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 108 | 120 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen -Training | Training | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 63 | 70 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Analysis of Piping Revisions | Procedure | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 27 | 40 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | DDC (Data Driven Construction) Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 945 | 2500 |  |  | after 60% 3D Model Review (not before) | 432181_Integrated System Specialist
Yes | Yes |  | Virtual Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - | 400 |  |  | optional | 432181_Integrated System Specialist
Yes | Yes |  | Augmented Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | Hold | Hold |  |  | optional | 432181_Integrated System Specialist
Yes | Yes |  | GEMAPI SA - Setting and Maintenance | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 54 | 60 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | GEMAPI SA - Training | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 63 | 70 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | MAGA (Material Management) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes | Yes |  | MAGA (Material Management) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 120 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 63 | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Completion Dossier - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Completion Dossier - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 54 | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Punch List - Training | Training | FABSI | System Completion | Spano Michele | Not started | 63 | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Hydro Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Pneumatic Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Flange Management Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Mechanical Completion Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 36 | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 27 | 40 |  |  |  | 430006_System Completion Coordinator
No | Yes |  | Carry Over Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 63 | 65 |  |  |  | 430006_System Completion Coordinator
Yes | No |  | Feasibility Study - Steel Structure (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | - | 1092 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | No |  | Feasibility Study - Piping (Prefabrication and Erection) | Procedure | FABSI | System Completion | Bardoscia Roberto | Not started | - | 2457 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | No |  | Feasibility Study - Piping support (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | - | 1638 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes | Yes |  | Supervision of Steel Structure Stick-Built (Vendor), only UAE Area | Supervision | FABSI | Production Engineering | Sandri Juri | Not started | - | 720 |  |  | consider 72 hours/monthly (40%) | 432186_Construction Engineer
- | - |  | Process Control for Piping Activities Procedure | - | - | - | - | -
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated for one year. Reply: 225 setting 720 manutenzione

## Kutei
Module | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours | Start date | Due date | Notes | Professional Role
Yes |  | Fabrication Execution Strategy | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 200 |  |  |  | XXXXXX_Fabrication Manager (Cannella)
Yes |  | Shop Drawing Steel Structure - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Piping - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 10 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Piping Support - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Steel Structure - Review (including TQ) | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 1680 |  |  | consider 140 hours/monthly (80%) | 432186_Construction Engineer
Yes |  | DPR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | ADR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Spooling Check List | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Spoolgen Setting - Setting and Maintenance | Software | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 120 |  |  |  | 432186_Construction Engineer
Yes |  | Spoolgen -Training | Training | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 70 |  |  |  | 432186_Construction Engineer
Yes |  | Analysis of Piping Revisions | Procedure | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 40 |  |  |  | 432186_Construction Engineer
Yes |  | DDC (Data Driven Construction) Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 2000 |  |  | after 60% 3D Model Review (not before) | 432181_Integrated System Specialist
Yes |  | Virtual Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 800 |  |  | optional | 432181_Integrated System Specialist
Yes |  | GEMAPI SA - Setting and Maintenance | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 540 |  |  |  | 432186_Construction Engineer
Yes |  | GEMAPI SA - Training | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 70 |  |  |  | 432186_Construction Engineer
Yes |  | MAGA (Material Management) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes |  | MAGA (Material Management) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | Preservation - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Preservation - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | CARP - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | CARP - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | WiTS (Welding Integrated Tracking System) - Setting and Maintenance STS (Spool Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 4560 |  |  | Data entry from remote | 432181_Integrated System Specialist
Yes |  | Support Management - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 540 |  |  |  | 432181_Integrated System Specialist
Yes |  | Support Management - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | Digital Test Pack - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Digital Test Pack - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Completion Dossier - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Completion Dossier - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Punch List - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Punch List - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Hydro Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Pneumatic Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Flange Management Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Mechanical Completion Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Punch List Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Carry Over Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 65 |  |  |  | 430006_System Completion Coordinator
11925

## Shah Gas
Stick-Built | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours (external) | Start date | Due date | Notes | Professional Role
Yes |  | Fabrication Setup | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 200 |  |  |  | XXXXXX_Fabrication Manager
Yes |  | Shop Drawing Steel Structure - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Piping - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 10 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Piping Support - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Shop Drawing Steel Structure - Review | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 840 |  |  | consider 140 hours/monthly (80%) | 432186_Construction Engineer
Yes |  | DPR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | ADR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Spooling Check List | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes |  | Spoolgen Setting - Setting and Maintenance | Software | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 120 |  |  |  | 432186_Construction Engineer
Yes |  | Spoolgen -Training | Training | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 70 |  |  |  | 432186_Construction Engineer
Yes |  | Analysis of Piping Revisions | Procedure | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 40 |  |  |  | 432186_Construction Engineer
Yes |  | DDC (Data Driven Construction) Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 2000 |  |  | after 60% 3D Model Review (not before) | 432181_Integrated System Specialist
Yes |  | Virtual Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | Hold |  |  | optional | 432181_Integrated System Specialist
Yes |  | Augmented Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | Hold |  |  | optional | 432181_Integrated System Specialist
Yes |  | GEMAPI SA - Setting and Maintenance | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 60 |  |  |  | 432186_Construction Engineer
Yes |  | GEMAPI SA - Training | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 70 |  |  |  | 432186_Construction Engineer
Yes |  | MAGA (Material Management) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes |  | MAGA (Material Management) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | Preservation - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Preservation - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | CARP - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | CARP - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | WiTS (Welding Integrated Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 120 |  |  |  | 432181_Integrated System Specialist
Yes |  | WiTS (Welding Integrated Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | STS (Spool Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  | includes hardware estimate | 432181_Integrated System Specialist
Yes |  | STS (Spool Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | Support Management - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Support Management - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes |  | Digital Test Pack - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Digital Test Pack - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Completion Dossier - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Completion Dossier - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Punch List - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes |  | Punch List - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes |  | Hydro Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Pneumatic Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Flange Management Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Mechanical Completion Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Punch List Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes |  | Feasibility Study - Steel Structure (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | 1092 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes |  | Feasibility Study - Piping (Prefabrication and Erection) | Procedure | FABSI | System Completion | Bardoscia Roberto | Not started | 2457 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes |  | Feasibility Study - Piping support (Prefabrication and Erection) | Procedure | FABSI | System Completion | Sandri Juri | Not started | 1638 |  |  | Deployment in according to the Org Chart Standard | 432186_Construction Engineer
Yes |  | Supervision of Steel Structure Stick-Built (Vendor), only UAE Area | Procedure | FABSI | System Completion | Sandri Juri | Not started | 720 |  |  | consider 72 hours/monthly (40%) | 432186_Construction Engineer
- |  | Process Control for Piping Activities Procedure | - | - | - | - | - | -
10927

## Venezia
Stick Built | Module | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours (external) | Start date | Due date | Notes | Professional Role
|  |  | Process Control for Piping Activities Procedure | Procedure | FABSI |  |  | Not started | 40
Yes | No |  | Fabrication Setup | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 100 |  |  |  | XXXXXX_Fabrication Manager (Cannella)
No | Yes |  | Fabrication Execution Strategy | Document | FABSI | Production Engineering | Cannella Antonio | Not started | 200 |  |  |  | XXXXXX_Fabrication Manager (Cannella)
Yes | Yes |  | Shop Drawing Steel Structure - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | - |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Shop Drawing Piping - Estimation | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | - |  |  |  | 432186_Construction Engineer
Yes | Yes |  | DPR Piping - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Spooling Check List | Document | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 20 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen Setting - Setting and Maintenance | Software | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | 120 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | Spoolgen -Training | Training | FABSI | Fabrication Engineering | Contreras Cesar Raul | Not started | - |  |  |  | 432186_Construction Engineer
Yes | Yes |  | DDC (Data Driven Construction) Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  | after 60% 3D Model Review (not before) | 432181_Integrated System Specialist
Yes | Yes |  | Virtual Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Augmented Reality - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | GEMAPI SA - Setting and Maintenance | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 60 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | GEMAPI SA - Training | Software | FABSI | Production Engineering | Bardoscia Roberto | Not started | 70 |  |  |  | 432186_Construction Engineer
Yes | Yes |  | MAGA (Material Management) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | MAGA (Material Management) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Preservation - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | CARP - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Tekla PowerFab - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Tekla PowerFab - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 120 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | WiTS (Welding Integrated Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | STS (Spool Tracking System) - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Support Management - Training | Training | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 70 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Digital Test Pack - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Completion Dossier - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | - |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Completion Dossier - Training | Training | FABSI | System Completion | Spano Michele | Not started | - |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List - Setting and Maintenance | Software | FABSI | Pre-Fabrication System | Gioso Alex | Not started | 60 |  |  |  | 432181_Integrated System Specialist
Yes | Yes |  | Punch List - Training | Training | FABSI | System Completion | Spano Michele | Not started | 70 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Hydro Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Pneumatic Test Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Flange Management Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Mechanical Completion Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Punch List Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 40 |  |  |  | 430006_System Completion Coordinator
No | Yes |  | Carry Over Procedure | Procedure | FABSI | System Completion | Spano Michele | Not started | 65 |  |  |  | 430006_System Completion Coordinator
Yes | Yes |  | Prefabrication Piping Stick Built - Baseline Schedule Review | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 50 |  |  |  | 432192_Work Phase Planner
Yes | Yes |  | Prefabrication Piping Stick Built - Schedule Preparation included study Direct and Indirect resources | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 100 |  |  |  | 432192_Work Phase Planner
No | Yes |  | Fabrication Module - Baseline Schedule Review | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started |  |  |  |  | 432192_Work Phase Planner
No | Yes |  | Fabrication Module - Schedule Preparation included study Direct and Indirect resources | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 200 |  |  |  | 432192_Work Phase Planner
Yes | Yes |  | Dynamic Visual Schedule Setting (Navis+P6, WBS wise) - Plant | Software | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 140 |  |  | Setup Execution (only) | 432192_Work Phase Planner
No | Yes |  | Dynamic Visual Schedule Setting - Fabrication Yard | Software | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 140 |  |  | Setup Execution (only) | 432192_Work Phase Planner

## Hold (hidden)
Stick Built | Module | Document Number | Activities | Title | Department | Technical Unit | Assigned to | Progress | Estimated hours (internal) | Estimated hours (external) | Start date | Due date | Notes | Professional Role
Yes | Yes |  | Prefabrication Piping Stick Built - Baseline Schedule Review | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 45 | 50 |  |  |  | 432192_Work Phase Planner
Yes | Yes |  | Prefabrication Piping Stick Built - Schedule Preparation included study Direct and Indirect resources | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 90 | 100 |  |  |  | 432192_Work Phase Planner
No | Yes |  | Fabrication Module - Baseline Schedule Review | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | [5 empty] | 432192_Work Phase Planner
No | Yes |  | Fabrication Module - Schedule Preparation included study Direct and Indirect resources | Schedule | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 180 | 200 |  |  |  | 432192_Work Phase Planner
Yes | Yes |  | Dynamic Visual Schedule Setting (Navis+P6, WBS wise) - Plant | Software | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 135 | 140 |  |  | Setup Execution (only) | 432192_Work Phase Planner
No | Yes |  | Dynamic Visual Schedule Setting - Fabrication Yard | Software | COTOS/COWOP | Construction Planning | Lopez Flores Jesus Hector | Not started | 135 | 140 |  |  | Setup Execution (only) | 432192_Work Phase Planner